## Sheet1
Item | Length | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18
Database Design | 2 Weeks | bar: 2019-10-14 to 2019-10-21
populate() function for client module | 4 Weeks | bar: 2019-10-21 to 2019-11-11
booking creation for client module | 3 Weeks | bar: 2019-11-11 to 2019-11-25
booking display for client module | 2 Weeks | bar: 2019-11-25 to 2019-12-02
finalisation / testing of client module | 1 Weeks | bar: 2019-12-02
reception view design (html/css) | 1 Weeks | bar: 2019-12-02 to 2019-12-09
reception view booking display script | 1 Weeks | bar: 2019-12-09
reception view patient details view | 3 Weeks | bar: 2019-12-16 to 2019-12-30
reception view booking details view | 3 Weeks | bar: 2020-01-06 to 2020-01-20
reception view bug fixes and testing | 6 Weeks | bar: 2020-01-13 to 2020-02-17
doctor view interface design | 3 Weeks | bar: 2020-02-24 to 2020-03-09
doctor view patient tools module | 4 Weeks | bar: 2020-03-09 to 2020-03-30
doctor view bug fixes and testing | 10 Weeks | bar: 2020-02-24 to 2020-04-27
overall testing and bug fixes | 6 weeks | bar: 2020-04-13 to 2020-05-18